## Blad1
ACTION POINTS SUPPORT PROJECT MSFD BG & RO
| Action | Responsible | Deadline | Status | Info
Note: NFCP (national focal contact points: Otilia & Georgi)
Formulated as outcome CBE JAN
1 | Initial agreement on template MFS by BG & RO; to continue work | NFCP, participating institutes | 2014-01-21 | ok
2 | Prioritisation of descriptors + responsible for programmes/ subprogrammes MFS | All | 2014-01-22 | ok
3 | Preparation CBE FEB - technical meeting public webpage (Bucharest): name IT specialist BG & RO + confirmation availability date (preferably 17/02; or back-up 21/02) | NFCP | 2014-01-28 | ok | Technical meeting on design of project & link to national webpages MSFD: content, structure, hosting details, etc.
4 | Preparation CBE FEB - check flights Denmark Varna for wk 17-21/02 | Joachim | 2014-01-28 | ok | Information to be provided to Violin
5 | Overview table BG & RO projects + involved institutes (based on input Laura) | ARCADIS/ involved institutes | 2014-01-29 | ok | sent to partners on the 04/02/2014
6 | Revision template monitoring factsheet according to WG Dike minutes (jan 2014) + reporting sheet (optimal synergy) / MFS programme level & subprogramme level | Joachim | 2014-01-29 | ok
7 | Final decision timeline monitoring process incl. consultation proces (duration, timing, format) + bilateral coordination between RO & BG | NFCP | 2014-01-29 | ok | Timeline proposed during CBE: Final MFS template (29/01), pilot project MFS (D5+D10) (21-22/02), completion MFS general + program level (15/04), translation (15/05), consultation (15/05 until 15/07), review MFS (15/08), administrative agreement (15/09), completion EC reporting (from 15/08 – 15/10); completion subprogramme MFS (15/04 til 15/09) Check potentials shorter consultation process (e.g. 1 month)
8 | List of monitoring programmes overview BG (~pres. Dan as example RO) | George | 2014-01-30 | ok | Document placed under map presentations CBE Jan (competent authorities BG)
9 | Take contact with ICES: proposed date CBE D3 - integrated monitoring first week of April (31/03 -04/04) + role ARC in prep ICES workshop + details programme + potential of 2nd workshop on Fisheries | NFCP/ Annemie | 2014-01-30 | ok | conference call with ICES planned on the 4th of February
10 | Revision of inception report (invitation process, names NFCP, roles NFCP (encouraging institutes), template invitation signed by directors + need for sending this revised version to EC/ Steering Group (mail EC)? Or to be included in progress report? | Annemie | 2014-01-30 | ok | contact taken with EC if a revised inception report is needed or if revisions can be done as part of progress report? EC confirmed to include changes/ revised documents as part of progress report (inception report considered as final)
11 | Preparation CBE FEB - technical meeting public webpage: meeting room (half day) in Bucharest + informing ARC on location as input invitation | Otilia | 2014-01-30 | ok | Hotel reservations made by Otilia for BG IT (not needed for ARCADIS)
12 | Preparation CBE FEB - practical organisation CBE completion pilot MFS (Wk 19-20/02; 2 MD, Varna, hotel info) + confirmation exact date | Vio | 2014-01-30 | ok | Inform Arcadis, COWI, experts BG & RO
13 | Preparation CBE FEB - confirmation of RO experts that will attend bilateral meeting (max. 3 RO experts reimbursement + Dan) | Dan/ Otilia | 2014-01-30 | ok | attendance from RO: Dan (as project partner) + 3 RO experts (that will be reimbursed - If Otilia is not coming, 3 experts from institutes can participate)
14 | Fine-tuning of timeline project | ARC | 2014-01-30 | ok | Including: Completion draft MFS (16/04/2014) Draft discussion doc BSC (01/09/2014) Final discussion doc BSC (01/11/2014)
15 | Revision contracts partners | ARC (Veronique)/ AVO | 2014-01-30 | ok | Note: Geoecomar & Dimitru Dorogan (~seperate invoicing adresses + reduced capacity of Mr. Dorogan)
16 | Final revision of the involved partners/lead of programme & subprogramme level (list completed during CBE Jan) | All | 2014-01-30 | ok | sent to partners on the 04/02/2014 to revise during unilateral MFS CBE
17 | Preparation CBE FEB - agenda; invitation unilateral + bilateral meeting | Annemie, Joachim; Vio/ Dan | 2014-01-30 | ok | Vio/ Dan: confirm experts BG & RO and their contact details Annemie/Joachim: prepare agenda + invitation
18 | Prep CBE funding opportunities: request for relevant info of EC | ARCADIS (Annemie) | 2014-02-01 | ok
19 | Final remarks on revised contracts by project partners + signed version to be sent (orginal by CBE march in Brussels) | Project partners | 2014-02-14 | ok
20 | CBE Pilot MFS - unilateral meeting of BG & RO | coordination by local PTE coord; attendance all relevant institutes | before 14/02/2014 | ok | Unilateral meetings take place in own country, and all relevant experts can be invited (no reimbursement as in own country) D5 - RO: Laura, Lummi, Dan D5- BG: Galina, Snejana D10 - RO: Anton D10- BG: Anton
21 | Outcome unilateral meeting of BG & RO to be exchanged (by local PTE coordinators) as preparation for bilateral CBE programme MFS | local PTE coord | 2014-02-14 | ok | Further distribution by Dan & Vio to other relevant institutes (incl. participants of bilateral CBE MFS)
22 | Overview table reported GES/ targets (~pres. George) | George (revision), Otilia | 2014-02-14 | ok | See example presentation George during CBE Jan
23 | Prep CBE technical meeting webpage - Take contact with EEA - content of EEA website | ARC (Wouter) | 2014-02-14 | ok
24 | CBE technical meeting web page design (Bucharest, 0,5 MD) | ARC BE, ARC RO, IT experts BG & RO | 2014-02-17 | ok
25 | CBE Pilot MFS - Bilateral meeting (in Varna): discussion on possilbe improvements template + coordination of pilot programme MFS + further planning completion MFS | RO & BG experts, Joachim | 17-22/02/2014 | ok
26 | Take contact with EEA project - data management for potential CBE in 2nd half 2014 (Deltares - Nikkie) | ARC (Wouter) | 2014-03-01 |  | Check contact details, minutes and other info by COWI if needed (Joachim attended first meeting)
27 | Presentation of timeline Monitoring process by BG & RO to EC (informal) on Back to Back meeting GES/ targets | NFCP | 2014-03-26 | ok
28 | SGM2 - Support project Black Sea + confirmation attendance & if ARCADIS need to arrange hotel bookings (Brussels) | NFCP, ARC, Dan, Violin | 2014-03-27 | ok | Confirmation received from NFCP + local PTE coordinators If hotel/flight bookings need to be done: please state exactly date of arrival & departure (depending on the meetings you will attend)
29 | CBE Funding opportunities (Brussels) | NFCP, ARC, Dan, Violin | 2014-03-28 | ok | Organized by ARCADIS + EC
Formulated as outcome CBE FEB + revised based on CBE MARCH
30 | Confirmation of room avaliability Constanta and participation as observer (Dan) in Varna CBE on 16+17 april | Dan | 2014-02-24 | ok
31 | Revise programme level MFS + indication of priority fields | Joachim | 2014-02-25 | ok
32 | Approval of general MFS by appropriate manager/ ministry | NFCP | No later than 07.03.2014 | ok | Before initiating remaining 11 MFS approval at the right level is recommended.
33 | Initiate 11 remaining programme level descriptors Local meeting for experts | Dan, Violin | On approval of MFS | ok | Suggestion: Local meeting for responsible experts to instruct in MFS completion
34 | Reformulation of common indicators in the monitoring fact sheets D5 & D10 + revision of GES/targets | Dan, Violin | 2014-04-07 | ok
35 | Revised sub-programme MFS_v2 | Joachim | 2014-04-07 | ok | To be coordinated with ARCADIS. Transferred to Excel format.
36 | Draft sub-programme MFS - activities_v2 | Joachim | 2014-04-07 | ok | Activities Subpgm MFS need partly changed format. To be coordinated with ARCADIS.
37 | Indicating priority fields within programme MFS | Joachim | 2014-04-07 | ok
38 | Sending available reviewed report on GES and targets to ARCADIS (if available) | NFCP | 2014-04-07 | to be checked | to be checked by COWI; as part of input programme MFS
39 | Further discussion on potential common indicators to make them common for D1/4/6 and D3 as a preparation to CBE integrated monitoring ICES | Dan, Violin + MS experts | 2014-04-07 | ok | During ICES CBE integrated monitoring
40 | Drafting the programme MFS for D1, (D4, D6) and D3 (focus on priority fields). | Dan, Violin + MS experts | 2014-04-09 | ok | To be sent to ICES in advance of the meeting by local PTE (09/04/2014)
41 | Exchange of presented spreadsheet funding opportunities BG | Georgi | 2014-04-10 | ok | Presented during CBE on funding opportunities
42 | Template action plan (needs) | ARC BE | 2014-04-15 | ok
43 | Template structuring funding (in general) + detailed template EMFF funding | ARC NL | 2014-04-15 | ok
44 | Completion of the draft final programme MFS for D5 and D10 (final revision) incl. agreed formulation on target (underlining indicator + parameters within brackets) | Dan, Violin | 2014-04-15 | ok | final drafts ready; need for final discussion in CBE July
45 | First draft remaining descriptors (priority fields) and exchange between BG/RO | Dan, Violin, local experts, NFCP | 2014-04-25 | ok | It is expected that the MFS will be finished at different times in the period 07.03.14 to 25.04.14. Coordination between BG and RO should take place as soon as a MFS is ready
46 | Second draft 11 remaining descriptors and exchange between BG/RO | Dan, Violin, local experts, NFCP | 2014-05-09 | ok | A period of 10 work days is forseen for this.
47 | Overview current status of funding used in the operational plans (based on templates provided by ARC NL) | NFCP | 2014-05-15 | in progress
48 | Draft final programme level MFS remaining descriptors | Dan, Violin, local experts, NFCP | 2014-05-15 | ok | need for final discussion in CBE July
49 | Drafting Pilot project MFS (subprogramme level) (D5+D10) | Dan, Violin, local experts, NFCP | 15/04/2014 - 15/06/2014 | in progress
50 | Final Approval subprogramme level MFS by appropriate authorities (based on revisions pilot subprogramme MFS) | NFCP + authorities | 2014-06-15 | postponed | proces to be coordinated by NFCP; question if approval authorities is still needed as subprogramme level does not go into consultation
51 | Translation programme level MFS | to be organized by BG & RO | 2014-06-15 | in progress | Start of translation of finsihed MFS (majority); if not ready, a limited number (max. 3) of MFS can be delivered two weeks later for translation (flexibility in process)
52 | Public consultation programme level MFS (EN) |  | 15/06/2014 - 15/07/2014 | postponed to 15/07/2014 - 15/08/2014 | 1 Month agreed between BG & RO
53 | Completion of the subprogram MFS (EN) | Dan, Violin, local experts, NFCP | 15/04/2014 - 15/09/2014 | postponed
54 | Review of the Programme level MFS | Dan, Violin, local experts, NFCP | 2014-08-15 | postponed | Agreed process between BG & RO; need for revision due to postponing of consultatio process
55 | Administrative agreement Programme level MFS | BG & RO authorities | 2014-09-15 | postponed | Agreed process between BG & RO; need for revision due to postponing of consultatio process
Formulated as outcome CBE APRIL + towards preparation of CBE JULY
56 | Draft final programme level MFS D1/4/6 & D3 descriptors | Dan, Violin, local experts, NFCP | 2014-05-15 | ok
57 | Draft final programme level MFS other descriptors (D2, D7,D8, D9, D11) | Dan, Violin, local experts, NFCP | 2014-06-01 | ok | BG: still to do D11: note: still fine-tuning needed as gaps have been identified by PTE
58 | QA/QC of draft final programme level MFS by PTE | COWI | 2014-06-10 | ok | still fine-tuning needed as gaps have been identified by PTE - agenda point CBE July
59 | Overview table GES/Targets/common parameters based on input of draft final programme level MFS | COWI | 2014-06-15 | ok | used as basis for further discussion on coordination during CBE july (back ground document)
60 | Revised sub-programme MFS_v3 | COWI | 2014-06-20 | ok | based on new info WG Dike reporting & discussion with David Connor (16/06/2014)
61 | Contact to be taken with Popi Pagou, JRC, Deltares in preparation of CBE oct (data management) | ARCADIS | 2014-06-23 | ok | regional workshop IRIS-SES Black Sea planned in Istanbul (back to back with BSC) - potential to be discussed to cooperate or to have represenation on both meetings by local PTE (note: CBEs only take place in BG or RO - linked to available project budget)
62 | Further discussion on common indicators with other relevant institutes during MISIS meeting | All relevant instittutes | 24-26/06/2014 | ok | attended by our local PTE/ NFCP
63 | Revision of responsibilities subprogramme level MFS | Dan, Violin, local experts, NFCP | 2014-06-30 | ok | as preparation to CBE July
64 | Drafting Pilot project MFS (subprogramme level) (D1 + D5) (preferably also D8 + D10) | Dan, Violin, local experts, NFCP | 2014-06-30 | done during CBE | as preparation to CBE July
Formulated as outcome CBE JULY
65 | Overview current status of funding used in the operational plans (based on templates provided by ARC NL) | NFCP | CBE July | ok | short overview to be given during CBE July
66 | Fine-tuning of programme level MFS descriptors | All | CBE July | ok
67 | Discussion completion process subprogramme level MFS | All | CBE July | ok | pilot cases: D1, D5 (D8, D10)
68 | Finalisation of table involved institutes per subpgm based on outcomes of CBE July | ARCADIS | 2014-07-08 | ok
69 | Revision of comparative analysis table based on revised input from Georgi & outcomes of discussion | COWI/ ARC | 2014-07-08 | ok
70 | Final check agreed parameters of the 11 descriptors (comparative analysis table) by all participating experts CBE July and NFCP | NFCP/ all experts | 2014-07-09
71 | Minutes CBE July | ARC | 2014-07-10 |  | incl annexes: table involved institutes, subpgm MFS sheet, etc.
72 | Extra effort to consult experts where no feedback has been received on programme MFS - D1 (seabirds) | BG:Vio RO: Otilia | 2014-07-10 |  | BG: Bulgarian Society for protection of Birds - contact: Anna Staneva (anna.staneva@bspb.org) Ro: Romanian Bird Society
73 | Consultation of expert (Dragos Micu) regarding revisions of RO MFS on seabed habitats | COWI | 2014-07-15 |  | e-mail consultation with Otilia as cc. Dead line dependent on availability of expert
74 | Revision & finalisation of programme MFS (EN) based on outcomes of CBE July: revised parameters, GES/ targets | Georgi, Dan | 2014-07-15
75 | Draft template of official involvement letter for relevant institutes to get support in completion of subpgr MFS (especially relevant for RO) | ARCADIS | 2014-07-12 |  | stating briefly process/timing + request for feedback on the parameters table and support to complete subprg MFS
76 | Formal invitation by mail to all relevant institutes for revision of tabel agreed parameters + support subpg MFS | NFCP | 2014-07-15 |  | in annex: agreed table on indicators annes: subpgrm list + relevant institutes
77 | List of institutes to whom we send/ have sent the MFS and agreed parameter table and from who we did/ did not get feedback | NFCP | 2014-07-15 |  | directors in cc Follow up of status feedback by NFCP (until deadlines set for feedback table + subpg MFS)
78 | Quality check MISIS webpage (consultation page) | ARCADIS | 2014-07-15 |  | support with extra descriptive text if needed
79 | Check official webpage BSBD for consultation purposes (link to be provided by Georgi) | ARCADIS/Georgi | 2014-07-15
80 | Revised structure discussion document BSC + input Violeta on input requested by whom (vision process) | Violetta | 2014-07-20
81 | First feedback from relevant institutes on agreed table parameters + name of contact who will give support for subpg MFS | All relevant instittutes | 2014-07-22 |  | name+relevant MFS can be included in list subpg
82 | Detailed mail to all contacts who will support subpg MFS with guidelines completing subpgm table (incl. additional questions to be sent to COWI) | COWI | 2014-07-30 |  | assistence by mailing/phoning to COWI
83 | Revision of already translated programme MFS according to changes made in Englisch programme MFS + sending final versions to ARCADIS for on EEA website | Georgi, Dan | depending on time setting consultation process
84 | uploading final programme MFS (EN) on EEA project webpage | ARCADIS | depending on time setting consultation process
85 | Finalisation of translation proces | Georgi, Dimitru, Dan | depending on time setting consultation process
86 | Contact with M. Papadoyannakis about reimbursement potential to have CBE in Istanbul (synergies with IRIS SES) | ARCADIS | 2014-07-20
87 | Start up of consultation - links of websites to be provided by NFCP | NFCP | 15/07 (BG) 01/08 (RO) |  | RO: start 1 aug (maybe 15/08) until 30 of aug (to 15/09) (depending on translation process) (link on National Administration RO waters and Grigore Antipa Institute webpage. Referring to MISIS webpage were actual documents can be downloaded) BG: start 15 july until 15 aug (link on BSBD webpage)
88 | First draft discussion document BSC | Violeta | 2014-08-29
89 | First Draft subprg MFS (subprogramme level) | Dan, Violin, local experts, NFCP | 2014-08-29
90 | Discussion on progress subprogramme level MFS | ARC/ COWI/ local PTE/ NFCP | 1st week september |  | conf call to be organised beginning september
91 | Discussion on progress discussion document BSC | Violeta/ NFCP/ Arcadis | 1st week september |  | conf call to be organised beginning september
92 | Review of the Programme level MFS (after consultation) | Dan, Violin, local experts, NFCP | 2014-09-15 |  | Agreed process between BG & RO; need for revision due to postponing of consultatio process
93 | Final draft discussion document BSC | Violeta | 2014-09-25 |  | timing to be discussed
94 | Administrative agreement Programme level MFS | BG & RO authorities | 2014-09-30 | new date to be confirmed | Agreed process between BG & RO; need for revision due to postponing of consultatio process
95 | Finalisation subprogramme level MFS | Dan, Violin, local experts, NFCP | 2014-09-30
96 | Presentation discussion document at BSC meeting | Violeta/ ARCADIS | 29/09-02/10/2014 | to be confirmed | planned in Istanbul (29/09 - 02/10/2014); to be confirmed
97 | date to be checked CBE OCT + SGM 3: data management + action plan based on outcomes of BSC meeting | All | 7-9/10/2014 | to be confirmed | planned in Varna (7-9/10/2014); check possibilities for synergies with IRIS-SES in Istanbul (agreement EC) or in Varna (with her as external expert)
98 | EC Reporting | NFCP | 2014-10-15 |  | Conform MSFD