## Blad1
ACTION POINTS SUPPORT PROJECT MSFD BG & RO
| Action | Responsible | Deadline | Status | Info
Note: NFCP (national focal contact points: Otilia & Georgi)
Formulated as outcome CBE JAN
1 | Initial agreement on template MFS by BG & RO; to continue work | NFCP, participating institutes | 2014-01-21 | ok
2 | Prioritisation of descriptors + responsible for programmes/ subprogrammes MFS | All | 2014-01-22 | ok
3 | Preparation CBE FEB - technical meeting public webpage (Bucharest): name IT specialist BG & RO + confirmation availability date (preferably 17/02; or back-up 21/02) | NFCP | 2014-01-28 | ok | Technical meeting on design of project & link to national webpages MSFD: content, structure, hosting details, etc.
4 | Preparation CBE FEB - check flights Denmark Varna for wk 17-21/02 | Joachim | 2014-01-28 | ok | Information to be provided to Violin
5 | Overview table BG & RO projects + involved institutes (based on input Laura) | ARCADIS/ involved institutes | 2014-01-29 | ok | sent to partners on the 04/02/2014
6 | Revision template monitoring factsheet according to WG Dike minutes (jan 2014) + reporting sheet (optimal synergy) / MFS programme level & subprogramme level | Joachim | 2014-01-29 | ok
7 | Final decision timeline monitoring process incl. consultation proces (duration, timing, format) + bilateral coordination between RO & BG | NFCP | 2014-01-29 | ok | Timeline proposed during CBE: Final MFS template (29/01), pilot project MFS (D5+D10) (21-22/02), completion MFS general + program level (15/04), translation (15/05), consultation (15/05 until 15/07), review MFS (15/08), administrative agreement (15/09), completion EC reporting (from 15/08 – 15/10); completion subprogramme MFS (15/04 til 15/09) Check potentials shorter consultation process (e.g. 1 month)
8 | List of monitoring programmes overview BG (~pres. Dan as example RO) | George | 2014-01-30 | ok | Document placed under map presentations CBE Jan (competent authorities BG)
9 | Take contact with ICES: proposed date CBE D3 - integrated monitoring first week of April (31/03 -04/04) + role ARC in prep ICES workshop + details programme + potential of 2nd workshop on Fisheries | NFCP/ Annemie | 2014-01-30 | ok | conference call with ICES planned on the 4th of February
10 | Revision of inception report (invitation process, names NFCP, roles NFCP (encouraging institutes), template invitation signed by directors + need for sending this revised version to EC/ Steering Group (mail EC)? Or to be included in progress report? | Annemie | 2014-01-30 | ok | contact taken with EC if a revised inception report is needed or if revisions can be done as part of progress report? EC confirmed to include changes/ revised documents as part of progress report (inception report considered as final)
11 | Preparation CBE FEB - technical meeting public webpage: meeting room (half day) in Bucharest + informing ARC on location as input invitation | Otilia | 2014-01-30 | ok | Hotel reservations made by Otilia for BG IT (not needed for ARCADIS)
12 | Preparation CBE FEB - practical organisation CBE completion pilot MFS (Wk 19-20/02; 2 MD, Varna, hotel info) + confirmation exact date | Vio | 2014-01-30 | ok | Inform Arcadis, COWI, experts BG & RO
13 | Preparation CBE FEB - confirmation of RO experts that will attend bilateral meeting (max. 3 RO experts reimbursement + Dan) | Dan/ Otilia | 2014-01-30 | ok | attendance from RO: Dan (as project partner) + 3 RO experts (that will be reimbursed - If Otilia is not coming, 3 experts from institutes can participate)
14 | Fine-tuning of timeline project | ARC | 2014-01-30 | ok | Including: Completion draft MFS (16/04/2014) Draft discussion doc BSC (01/09/2014) Final discussion doc BSC (01/11/2014)
15 | Revision contracts partners | ARC (Veronique)/ AVO | 2014-01-30 | ok | Note: Geoecomar & Dimitru Dorogan (~seperate invoicing adresses + reduced capacity of Mr. Dorogan)
16 | Final revision of the involved partners/lead of programme & subprogramme level (list completed during CBE Jan) | All | 2014-01-30 | ok | sent to partners on the 04/02/2014 to revise during unilateral MFS CBE
17 | Preparation CBE FEB - agenda; invitation unilateral + bilateral meeting | Annemie, Joachim; Vio/ Dan | 2014-01-30 | ok | Vio/ Dan: confirm experts BG & RO and their contact details Annemie/Joachim: prepare agenda + invitation
18 | Prep CBE funding opportunities: request for relevant info of EC | ARCADIS (Annemie) | 2014-02-01 | ok
19 | Final remarks on revised contracts by project partners + signed version to be sent (orginal by CBE march in Brussels) | Project partners | 2014-02-14 | ok
20 | CBE Pilot MFS - unilateral meeting of BG & RO | coordination by local PTE coord; attendance all relevant institutes | before 14/02/2014 | ok | Unilateral meetings take place in own country, and all relevant experts can be invited (no reimbursement as in own country) D5 - RO: Laura, Lummi, Dan D5- BG: Galina, Snejana D10 - RO: Anton D10- BG: Anton
21 | Outcome unilateral meeting of BG & RO to be exchanged (by local PTE coordinators) as preparation for bilateral CBE programme MFS | local PTE coord | 2014-02-14 | ok | Further distribution by Dan & Vio to other relevant institutes (incl. participants of bilateral CBE MFS)
22 | Overview table reported GES/ targets (~pres. George) | George (revision), Otilia | 2014-02-14 | ok | See example presentation George during CBE Jan
23 | Prep CBE technical meeting webpage - Take contact with EEA - content of EEA website | ARC (Wouter) | 2014-02-14 | ok
24 | CBE technical meeting web page design (Bucharest, 0,5 MD) | ARC BE, ARC RO, IT experts BG & RO | 2014-02-17 | ok
25 | CBE Pilot MFS - Bilateral meeting (in Varna): discussion on possilbe improvements template + coordination of pilot programme MFS + further planning completion MFS | RO & BG experts, Joachim | 17-22/02/2014 | ok
26 | Take contact with EEA project - data management for potential CBE in 2nd half 2014 (Deltares - Nikkie) | ARC (Wouter) | 2014-03-01 |  | Check contact details, minutes and other info by COWI if needed (Joachim attended first meeting)
27 | Presentation of timeline Monitoring process by BG & RO to EC (informal) on Back to Back meeting GES/ targets | NFCP | 2014-03-26 | ok
28 | SGM2 - Support project Black Sea + confirmation attendance & if ARCADIS need to arrange hotel bookings (Brussels) | NFCP, ARC, Dan, Violin | 2014-03-27 | ok | Confirmation received from NFCP + local PTE coordinators If hotel/flight bookings need to be done: please state exactly date of arrival & departure (depending on the meetings you will attend)
29 | CBE Funding opportunities (Brussels) | NFCP, ARC, Dan, Violin | 2014-03-28 | ok | Organized by ARCADIS + EC
Formulated as outcome CBE FEB + revised based on CBE MARCH
30 | Confirmation of room avaliability Constanta and participation as observer (Dan) in Varna CBE on 16+17 april | Dan | 2014-02-24 | ok
31 | Revise programme level MFS + indication of priority fields | Joachim | 2014-02-25 | ok
32 | Approval of general MFS by appropriate manager/ ministry | NFCP | No later than 07.03.2014 | ok | Before initiating remaining 11 MFS approval at the right level is recommended.
33 | Initiate 11 remaining programme level descriptors Local meeting for experts | Dan, Violin | On approval of MFS |  | Suggestion: Local meeting for responsible experts to instruct in MFS completion
34 | Reformulation of common indicators in the monitoring fact sheets D5 & D10 + revision of GES/targets | Dan, Violin | 2014-04-07
35 | Revised sub-programme MFS | Joachim | 2014-04-07 |  | To be coordinated with ARCADIS. Transferred to Excel format.
36 | Draft sub-programme MFS - activities | Joachim | 2014-04-07 |  | Activities Subpgm MFS need partly changed format. To be coordinated with ARCADIS.
37 | Indicating priority fields within programme MFS | Joachim | 2014-04-07
38 | Sending available reviewed report on GES and targets to ARCADIS (if available) | NFCP | 2014-04-07
39 | Further discussion on potential common indicators to make them common for D1/4/6 and D3 as a preparation to CBE integrated monitoring ICES | Dan, Violin + MS experts | 2014-04-07 |  | During ICES CBE integrated monitoring
40 | Drafting the programme MFS for D1, (D4, D6) and D3 (focus on priority fields). | Dan, Violin + MS experts | 2014-04-09 |  | To be sent to ICES in advance of the meeting by local PTE (09/04/2014)
41 | Exchange of presented spreadsheet funding opportunities BG | Georgi | 2014-04-10 |  | Presented during CBE on funding opportunities
42 | Template action plan (needs) | ARC BE | 2014-04-15
43 | Template structuring funding (in general) + detailed template EMFF funding | ARC NL | 2014-04-15
44 | Completion of the final programme MFS for D5 and D10 (final revision) incl. agreed formulation on target (underlining indicator + parameters within brackets) | Dan, Violin | 2014-04-15
45 | First draft remaining descriptors (priority fields) and exchange between BG/RO | Dan, Violin, local experts, NFCP | 2014-04-25 |  | It is expected that the MFS will be finished at different times in the period 07.03.14 to 25.04.14. Coordination between BG and RO should take place as soon as a MFS is ready
46 | Second draft 11 remaining descriptors and exchange between BG/RO | Dan, Violin, local experts, NFCP | 2014-05-09 |  | A period of 10 work days is forseen for this.
47 | Overview current status of funding used in the operational plans (based on templates provided by ARC NL) | NFCP | 2014-05-15
48 | Final programme level MFS remaining descriptors | Dan, Violin, local experts, NFCP | 2014-05-15
49 | Drafting Pilot project MFS (subprogramme level) (D5+D10) | Dan, Violin, local experts, NFCP | 15/04/2014 - 15/06/2014
50 | Final Approval subprogramme level MFS by appropriate authorities (based on revisions pilot subprogramme MFS) | NFCP + authorities | 2014-06-15 |  | proces to be coordinated by NFCP
51 | Translation programme level MFS | to be organized by BG & RO | 2014-06-15 |  | Start of translation of finsihed MFS (majority); if not ready, a limited number (max. 3) of MFS can be delivered two weeks later for translation (flexibility in process)
52 | Public consultation programme level MFS (EN) |  | 15/06/2014 - 15/07/2014 |  | 1 Month agreed between BG & RO
53 | Completion of the subprogram MFS (EN) | Dan, Violin, local experts, NFCP | 15/04/2014 - 15/09/2014
54 | Review of the Programme level MFS | Dan, Violin, local experts, NFCP | 2014-08-15 |  | Agreed process between BG & RO
55 | Administrative agreement Programme level MFS | BG & RO authorities | 2014-09-15 |  | Agreed process between BG & RO
56 | EC Reporting | NFCP? | 2014-10-15 |  | Conform MSFD