## CBE planning
| Meetings (Steering group/ capacity building events) | [14 empty] | Location | Date | Timing | Invited/ confirmed Participants | [6 empty] | Reimbursement
|  | Dec | Jan | Feb | Mrch | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |  |  |  | International PTE | Local PTE BG | Local PTE RO | NFCP | BG experts | RO experts | external experts | PTE | BG experts | RO experts
| Kick-off meeting - Brussels | [14 empty] | Brussels (BE) | 2013-12-17 | 1 MD | VAD, AVO, WRO | VRA | DVA | OMI, GPA, VRO | bar: Dec
| CBE JAN | [14 empty] | Constanta (RO) | 2014-01-21 | bar: Jan
| Project team meeting | [14 empty] | Constanta (RO) | 2014-01-21 | 0,25 MD | AVO, JRL | VRA, GSH | DVA, MMU, MGO, ATE, DDO | OMI, GPA | IO-BAS (GSH) | Geoecomar, NIMRD |  | AVO, JRL, VRA, DVA | GSH, GPA | none (host country) | bar: Jan
1 | CBE1: Discussion on the template monitoring fact sheet (Task 1.1) | [14 empty] | Constanta (RO) | 21-22/01/2014 | 0,5 MD | AVO, JRL | VRA, GSH | DVA, MMU, MGO, ATE, DDO | OMI, GPA | IO-BAS (GSH) | Geoecomar, NIMRD |  | AVO, JRL, VRA, DVA | GSH, GPA | none (host country) | bar: Jan
2 | CBE2: Status & main issues on monitoring BG & RO (Task 1.1) | [14 empty] | Constanta (RO) | 21-22/01/2014 | 0,5 MD | AVO, JRL | VRA, GSH | DVA, MMU, MGO, ATE, DDO | OMI, GPA | IO-BAS (GSH) | Geoecomar, NIMRD |  | AVO, JRL, VRA, DVA | GSH, GPA | none (host country) | bar: Jan
3 | CBE3: Review and prioritization technical and research needs for BG & RO (Task 1.2) | [14 empty] | Constanta (RO) | 21-22/01/2014 | 0,5 MD | AVO, JRL | VRA, GSH | DVA, MMU, MGO, ATE, DDO | OMI, GPA | IO-BAS (GSH) | Geoecomar, NIMRD |  | AVO, JRL, VRA, DVA | GSH, GPA | none (host country) | bar: Jan
4 | CBE4: Needs for data information sharing (public web page) (Task 1.4) | [14 empty] | Constanta (RO) | 21-22/01/2014 | 0,5 MD | AVO, JRL | VRA, GSH | DVA, MMU, MGO, ATE, DDO | OMI, GPA | IO-BAS (GSH) | Geoecomar, NIMRD |  | AVO, JRL, VRA, DVA | GSH, GPA | none (host country) | bar: Jan
| CBE FEB | [14 empty] | RO & BG | 17-21/02/2014 | bar: Feb
5 | CBE5: Technical meeting public webpage (Task 1.4) - IT specialists | [14 empty] | Bucharest (RO) | 17 or 21/02/2014 | 0,5 MD | JTA, ARC Ro |  |  |  | Krasimir Todorov | IT specialist RO |  | JTA | IT specialist BG | none (host country) | bar: Feb
6 | CBE6: Completion pilot monitoring fact sheets (Task 1.1) (unilateral work session) | [14 empty] | Con (RO) & Varna (BG) | Before 17/02/14 | 1 MD |  | GSH | DVA | GPA | IO-BAS, etc. | Geoecomar, NIMRD |  |  | none (host country) | none (host country) | bar: Feb
7 | CBE7: Final Template monitoring sheet (consultation & agreement) based on pilot cases descriptors | [14 empty] | Varna (BG) | 19-20/02/2014 | 0,5 MD | JRL | VRA, GSH | DVA | GPA | IO-BAS, etc. | NIMRD (Lumi, Anton, ?) |  | JRL, VRA, DVA | none (host country) | 3 experts (Lumi, Anton, ?) | bar: Feb
8 | CBE8: Coordination & further impletion monitoring fact sheets (Task 1.1) (bilateral work session) | [14 empty] | Varna (BG) | 19-20/02/2014 | 1,5 MD | JRL | VRA, GSH | DVA | GPA | IO-BAS, etc. | NIMRD (Lumi, Anton, ?) |  | JRL, VRA, DVA | none (host country) | 3 experts (Lumi, Anton, ?) | bar: Feb
| SGM 2 - CBE March | [14 empty] | Brussels (BE) | 27-28/03/2014 | bar: Mrch
| Steering Group meeting SGM 2 | [14 empty] | Brussels (BE) | 2014-03-27 | 0,5 MD | AVO | VRA | DVA | OMI, GPA |  |  |  | JKL, VRA, DVA | GPA | OMI | bar: Mrch
9 | CBE9: Discussion results review GES and targets (Art. 9 & 10) | [14 empty] | Brussels (BE) | 2014-03-28 | 0,5 MD | AVO, JKL | VRA | DVA | OMI, GPA | none | none |  | JKL, VRA, DVA | GPA | OMI | bar: Mrch
10 | CBE10: Potential funding opportunities to address identified needs BSC (Task 1.2) | [14 empty] | Brussels (BE) | 2014-03-28 | 0,5 MD | AVO, JKL | VRA | DVA | OMI, GPA | none | none |  | JKL, VRA, DVA | GPA | OMI | bar: Mrch
| CBE April (ICES) | [14 empty] | Con (RO) & Varna (BG) | 14-17/04/2014 | bar: Apr
11a | CBE11a: Integrated monitoring BG & RO (Task 1.1) | [14 empty] | Constanta (RO) | 14-15/04/2014 | 1 MD |  | VRA (observer) | DVA, MMU, MGO, ATE, DDO | OMI | All relevant institutes | All relevant institutes | ICES | WRO | VRA | none (host country) | bar: Apr
11b | CBEb: Financing of monitoring infrastructure BG & RO (ICES) | [14 empty] | Constanta (RO) | 14-15/04/2014 | 1 MD |  | VRA (observer) | DVA, MMU, MGO, ATE, DDO | OMI | All relevant institutes | All relevant institutes | ICES | WRO | VRA | none (host country) | bar: Apr
11a | CBE11a: Integrated monitoring BG & RO (Task 1.1) | [14 empty] | Varna (BG) | 16-17/04/2014 | 1 MD | WRO | VRA | DVA (observer) | GPA | 2 extra BG expert | All relevant institutes | ICES | WRO | none (host country) | DVA | bar: Apr
11b | CBEb: Financing of monitoring infrastructure BG & RO (ICES) | [14 empty] | Varna (BG) | 16-17/04/2014 | 1 MD | WRO | VRA | DVA (observer) | GPA | 2 extra BG expert | All relevant institutes | ICES | WRO | none (host country) | DVA | bar: Apr
| SGM 3 - CBE June | [14 empty] | Constanta (RO) | 24-26/06/2014 | bar: Jun
12 | CBE12: Draft work plan technical & research needs BG & RO | [14 empty] | Constanta (RO) | 24-26/06/2014 | 1 MD | AVO | VRA, GSH | DVA | OMI, GPA | To be decided | To be decided | bar: Jun
13 | CBE13: Work session on completion subprogramme MFS | [14 empty] | Constanta (RO) | 24-26/06/2014 | 1 MD | JRL | VRA, GSH | DVA | OMI, GPA | To be decided | To be decided | bar: Jun
| CBE Oct | [14 empty] | Istanbul | 2014-10-03
14 | CBE14: Presentation discussion document to Black Sea Commission | [14 empty] | Istanbul | 2014-10-03 | 1 MD | AVO? | Violeta Velikova | [5 empty] | AVO, VVE
| SGM 4 - CBE Oct | [14 empty] | Varna (BG) | 07-09/10/2014 | bar: Oct
| Steering Group meeting SGM 3 | [14 empty] | Varna (BG) | 07-09/10/2014 | 0,5 MD | WRO | VRA | DVA | OMI, GPA | bar: Oct
15 | CBE15: (Monitoring) Data comparability & management (Task 1.1) | [14 empty] | Varna (BG) | 07-09/10/2014 | 1 MD | WRO | VRA, GSH | DVA | OMI, GPA | To be decided | To be decided | JRC | bar: Oct
16 | CBE16: Finlisation work plan technical & research needs BG & RO | [14 empty] | Varna (BG) | 07-09/10/2014 | 0,5 MD | WRO | VRA | DVA | OMI, GPA | To be decided | To be decided | bar: Oct
| Final Steering group meeting | [14 empty] | Brussels (BE) | 2015-01-15 | 1 MD | AVO | VRA | DVA | OMI, GPA |  |  |  | VRA, DVA | GPA | OMI
Subject to availability of room/person
Expert table (names - function)
ARCADIS BE
AVO | Annemie Volckaert | Dec: Senior
WRO | Wouter Rommens | Dec: Senior
JLA | Johan Lammerant | Dec: Senior
VAD | Veronique Adriaenssens | Dec: Senior
RDU | Riet Durinck | Dec: Junior
RPE | Richard Peters | Dec: Junior
SBO | Sarah Bogaert | Dec: Senior
JTA | Jan Tanghe | Dec: Senior
ARC RO | Arcadis Romania (IT specialists) | Dec: Junior
ARCADIS BE -SUBCONTRACTING LOCAL EXPERTS
VRA | Violin Raykov | Dec: Senior; Jan: IO-BAS; Mrch: BG; Apr: Varna
GSH | Galina Shtereva | Dec: Senior; Jan: IO-BAS; Mrch: BG; Apr: Varna
VVE | Violeta Velikova | Dec: Senior; Jan: SURDEP; Mrch: BG; Apr: S-Africa
DDO | Dimitri Dorogan | Dec: Senior; Mrch: RO
Remarks Dimitri (mail 25/11/2013)
also Mare Nostrum, GSP Offshore S.A (Black Sea offshore oil riggs exploitation)
COWI
JRL | Joachim Raben-Levetzau | Dec: Senior
EPO | Erling Poulsen | Dec: Senior
TTA | Thomas Torp Andersen | Dec: Senior
CJU | Carsten Jürgensen | Dec: Senior
MHJ | Morten Hjorth | Dec: Senior
Remarks COWI (mail JRL 19/11/2013)
With regards to a pool of experts COWI is able to contribute to the items below. All the experts are senior. Please note that the CVs of my colleagues were not submitted with the proposal.
(x) I have knowledge of the implementation of D2 and D9 although I am not an expert in either. However, D2 is more a matter of introduction vector handling and control, than specific knowledge of the actual species. The effect of non-indigenous species is relevant for status assessments but requires local knowledge – and there is not much you can do about it anyway, once they are there. D9 is the odd and only partly relevant descriptor and has to my knowledge been treated as such by most MS. EU legislation puts limits on contaminants in seafood, but control usually takes place within the processing industry and the link to the marine environment is normally impossible to establish.
**D1 appears to be well covered already. D4 is complicated and need to be discussed further.
CMRC
DDU | Declan Dunne | Dec: Senior
STW | Sarah Twomey | Dec: Senior
MJE | Mark Jessop | Dec: Senior; Jan: Sea birds
GSU | Gerry Sutton | Dec: Senior
TDO | Tom Doyle | Dec: Senior
ARCADIS NL
THU | Tanya Huizer | Dec: Junior
RSN | Roelant Snoek | Dec: Senior
BKA | Belinda Kater | Dec: Senior
JKL | Jeroen Klooster | Dec: Senior
GEOECOMAR
DVA | Dan Vasiliu | Dec: Senior; Mrch: RO
MMU | Mihaela Muresan | Dec: Junior; Mrch: RO
MGO | Marian T. Gomoiu | Dec: Senior; Mrch: RO
ATE | Adrian Teaca | Dec: Senior; Mrch: RO
Remarks Dan (mail 25/11/2013)
In terms of Descriptor 11, i have to mention that there is not a monitoring program in Romania for underwater noise, just some experimental studies developed by the "Mircea cel Batran" Naval Academy, Geoecomar (Prof Gomoiu) and NIMRD.
NFCP | National Focal Contact Points
OMI | Otilia Mihail
GPA | Georgi Parlichev
VRO | Violetta Royachka