## Slide 1
EAGLE kick-off meeting (SC 59142)
24.10.2022
WENR - EAGLE Kick-off meeting
Task 6: Use of AI/ML EO-based analytics products for filling gaps in CLC+ instances (CLC Legacy and/or LULUCF)

## Slide 2
Task 6: Use of AI/ML EO-based analytics products for filling gaps
Expected output:
  Data gap typology overview
  Methodology overview for filling the data gaps
  Proposal for common practice of filling data gaps – from identification through typology to solution
  Guideline for selection of data gaps filling method
Actions
  Make inventory of data gaps for CLC+ LULUCF (also Legacy (if existing)): what type of data is missing (data gap typology) - outputs of tasks 15, 16, 17 and 22 (WENR 2, Lechner 1 – 28. 2. 2023)
  Define typology of data gaps (WENR 2 – 28. 2. 2023)
    Thematic – based missing classes
    Methodological – based on used approaches which results in data gaps
    Source data oriented – based on used data source which results in data gaps
  Inventory of datasets to be used to fill LU gaps: EO-based products, CLMS data sets, other spatial data (WENR 2, Specto Natura 2 – 28. 2. 2023)

## Slide 3
Actions
  Review the usefulness of commercially available analytics layers to support gap filling (Specto Natura 13 – 31. 3. 2023)
  Evaluations of suitability of AI/ML methods for gap filling – which approach to use to fill the gaps (30. 4. 2023)
    Selection of methodology based on typology and available data (WENR 2)
    Selection and collecting of data for case study area (WENR 3, UBA 2, UMA 2, DGT 1)
    Developing of AI/ML models (WENR 8)
  Test specific methodologies in case study areas for certain gaps (30. 11. 2023)
    Run AI/ML models (WENR 5)
    Get feedback and validate results by experts/partners (Lechner 1, UBA 3, UMA 2, DGT 2, M. Bock 2)
  Suggest method for upscaling to EU level (WENR 1 - 30. 11. 2023)
Task 6: Use of AI/ML EO-based analytics products for filling gaps

## Slide 4
Milestones
  M1 Overview of data gaps extent / typology, input layers for gap filling and methodology (30. 4. 2023)
  M2 Application of gap filling algorithm in case study areas (20. 9. 2023)
Deliverables
    D6-1 (30. 11. 2023): Report of Task 6 - Use of AI/ML and other (commercial) EO-based analytics for filling gaps in CLC+ instances
Partners
  WENR (25), Lechner (2), Specto Natura (15), M. Bock (2), UBA (5), UMA (4), DGT (3)
Task 6: Use of AI/ML EO-based analytics products for filling gaps

## Slide 5
First results (to be filled after the KOM)
Action | Symbol | Remark
Content agreed |  | 
Subtasks agreed |  | 
Milestones agreed |  | 
Deliverable agreed |  | 
AOB |  | 

## Slide 6
Short summary for next steps, meetings or other relevant issues
Xxx