# Text boxes

# Project Progress

| Initiating | Planning | Executing | Closing |
| --- | --- | --- | --- |
|  | Monitor & Control |  |

Overall Status: Green

Project Owner (PO): Peter Loeffler

Business Manager (BM): Annemarie Bastrup-Birk

Solution Provider (SP): Christian-Xavier Prosperini

Project Manager (PM): Miruna Badescu

# Milestones

<08/07/18>: Static portal with design

<30/09/18>: First test version of the infrastructure

<01/02/19>: First prototype ready for testing

<31/12/19>: Final prototype ready and operational ready at the end of the contract

# Project Indicators

Schedule: Green

- Baselined delivery date: 12/2019

- Forecasted delivery date: 12/2019

- Variance: 0 months

Cost: Green

- Baselined: 1659 (1129 EdW+530 TRACASA) workdays

- Spent: 129 (97 EdW + 32 TRACASA) workdays

- Forecasted: 129 workdays

- Variance: 0% (Forecasted - Baselined)

# Project Changes (input from Change Log)

Status: Green

- Severe: 0

# Project Status Summary

Project has just exited the planning phase, expecting approval of delivered planning phase documents and execution of the project’s tasks already started.

Web design of the static portal is up&running. Assessment of the datasets is still ongoing; some maps and Tableau analysis have been made available. Use cases definition is on-going.

# Activities Performed and Planned

Performed:

- Data transfer from JRC to EEA, status complete

- Static portal with design, status complete

- Project Management – Initiation and Planning, status ongoing

Planned:

- First test version of the infrastructure

# Risks (input from Risk Log)

Status: Green

- Active: 0

# Issues (input from Issue Log)

Status: Green

- Urgent: 1

- Id 1, size 3=Medium, severity 3=Medium -