## Sheet1
ID | Category | Title | Description | Status | Identified by | Identification Date | Action Details (effort & responsible) | Urgency | Impact | Size | Target Date | Issue owner | Escalation (Yes/No) | Traceability and Comments
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Datasets | Availability of meaningful datasets | ICP datasets have been identified as being a good datasource and should be collected from the institution | Open | Miruna Badescu | 22/06/2018 | Miruna - contact ICP with the request of data EEA - progress with the agreement with ICP | 3=Medium | 4=High | 3=Medium | 30/08/2018 |  | No | Workpackage 2 Workpackage 3
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
Note on B1: Author: Issue category related to the area affected by the issue
Note on C1: Author: Short title for the issue.
Note on D1: Author: A description of the issue and its impact
Note on E1: Author: The issue status can be any of the following: Open: the issue has been identified and requires attention and, if possible, a resolution. Postponed: this status is set if resolving the issue is postponed due to other priorities. Resolved: this status indicates that all necessary actions are completed and the issue is resolved. Closed: this status indicates that all work is completed and verified. The issue can then be marked as closed.
Note on F1: Author: The name of the person who identified the issue.
Note on G1: Author: The date on which the issue was raised.
Note on H1: Author: Description of the recommended action, and the steps, deliverables, timescale, resources and effort involved.
Note on I1: Author: A numerical value denoting how urgent the issue is. The possible values are: 5=Very high, 4=High, 3=Medium, 2=Low, 1=Very low
Note on J1: Author: A numerical value denoting the issue’s impact. The possible values are: 5=Very high, 4=High, 3=Medium, 2=Low, 1=Very low
Note on K1: Author: Issue size represents the effort needed to resolve the issue. The possible values are: 5=Very high, 4=High, 3=Medium, 2=Low, 1=Very low
Note on L1: Author: The date on which the issue is expected to be resolved.
Note on M1: Author: The person accountable for resolving the issue.
Note on N1: Author: Whether or not the issue is to be escalated to the Directing or Steering Layers (Yes or No).
Note on O1: Author: The ID(s) of the tasks (in the Project Work Plan) that implement the issue actions, and/or the IDs of related changes, risks or decisions (Log entries). Also include any additional information/comments related to the issue.

## Sheet2
Category value | Status
Business | Open | 5=Very high
IT | Postponed | 4=High
People & organisation | Resolved | 3=Medium
External | Closed | 2=Low
Legal |  | 1=Very low
Datasets