# Project Progress

|  |  |  |  |
| --- | --- | --- | --- |
| Initiating | Planning | Executing | Closing |
|  | Monitor & Control |  |

**Overall Status: Green**

**Project Owner (PO): Cristina Brăilescu, DG ENV**

**Business Manager (BM):** **Beate Werner, EEA**

**Solution Provider (SP): Soren Roug, EEA**

**EEA Project Manager: Nils Hettich, EEA**

**EdW Project Manager (PM):** **Miruna Badescu, EdW**

**EdW Technical Lead: Mihai Macaneata, EdW**

# Milestones

08/07/18: Static portal with design

14/09/18: First test version of the infrastructure

28/02/19: First prototype ready for testing

31/12/19: Final prototype ready and operational ready

04/02/20: Launch of FISE prototype

31/08/20: Improvements and enhancements of the prototype

30/11/20: Maintenance of FISE

# Project Indicators

Schedule: **Green**

* Baselined delivery date: 08/2020
* Forecasted delivery date: 08/2020
* Variance: 0 months

Cost: **Green** (until 31/05/2020)

* Baselined: 1129 man-days
* Spent: 1019,375 man-days
* Forecasted: 1019,375 man-days
* Variance: 0% (Forecasted - Baselined)

# Project Changes (input from Change Log)

Status: **Green**

* Severe: 0

# Project Status Summary

All work that has been performed during the reporting period has been discussed, prioritized and assigned in very close cooperation with EEA Project Manager. A complete list of activities can be consulted [here](https://taskman.eionet.europa.eu/time_entries?utf8=%E2%9C%93&set_filter=1&sort=spent_on%3Adesc&f%5B%5D=spent_on&op%5Bspent_on%5D=%3E%3C&v%5Bspent_on%5D%5B%5D=2020-04-01&v%5Bspent_on%5D%5B%5D=2020-05-31&f%5B%5D=cf_36&op%5Bcf_36%5D=%3D&v%5Bcf_36%5D%5B%5D=eaudeweb-FISE-07.0202%2F2018%2F776035%2FSER%2FENV.D.1&f%5B%5D=&c%5B%5D=project&c%5B%5D=spent_on&c%5B%5D=user&c%5B%5D=activity&c%5B%5D=issue&c%5B%5D=comments&c%5B%5D=hours&group_by=&t%5B%5D=hours&t%5B%5D=).

Work has been prioritised and agreed for 3rd June release of FISE and discussions have taken place for future needs of FISE, as we are approaching the end of the specific contract, which mainly consists of: improvements of already developed features, integration of Art 17 data and maintenance of the portal.

# Issues (input from Issue Log)

Status: **Green**

# Risks (input from Risk Log)

Status: **Green**

# Activities Performed and Planned

Performed:

* Improvements of the mosaic tiles layouts for Volto toolkit
* Creation of PloneSaaS orchestration for FISE, automatic deployment for demo-forest frontend and other DevOp tasks
* Improvements for Plotly chart tool
* Adding news component to FISE and corresponding portlet
* Re-Implementation of the catalogue search in ESBootstrap and creation of the file structure for NFI repository using CMShare
* Setup tests and Jenkins pipelines for the Nodejs/React Volto add-ons

Planned:

* Agree with EEA Project Manager on the future scope and prioritisation of work for FISE and their implementation (e.g.: search, catalogue, usage of JRC collected data, enhancements, improvements, export blocks in pdf, normalisation of data sources which feed the factsheets etc.)
* Bi-Monthly status report