# Project Progress

|  |  |  |  |
| --- | --- | --- | --- |
| Initiating | Planning | Executing | Closing |
|  | Monitor & Control |  |

**Overall Status: Green**

**Project Owner (PO): Cristina Brăilescu, DG ENV**

**Business Manager (BM):** **Beate Werner, EEA**

**Solution Provider (SP): Soren Roug, EEA**

**EEA Project Manager: Nils Hettich, EEA**

**EdW Project Manager (PM):** **Miruna Badescu, EdW**

**EdW Technical Lead: Mihai Macaneata, EdW**

# Milestones

08/07/18: Static portal with design

14/09/18: First test version of the infrastructure

28/02/19: First prototype ready for testing

31/12/19: Final prototype ready and operational ready

04/02/20: Launch of FISE prototype

31/08/20: Improvements and enhancements of the prototype

01/09 - 30/11/20: Maintenance of FISE

# Project Indicators

Schedule: **Green**

* Baselined delivery date: 08/2020
* Forecasted delivery date: 08/2020
* Variance: 0 months

Cost: **Green** (until 31/07/2020)

* Baselined: 1129 man-days
* Spent: 1070,875 man-days
* Forecasted: 1070,875 man-days
* Variance: 0% (Forecasted - Baselined)

# Project Changes (input from Change Log)

Status: **Green**

* Severe: 0

# Project Status Summary

All work that has been performed during the reporting period has been discussed, prioritized and assigned in very close cooperation with EEA Project Manager. A complete list of activities can be consulted [here](https://taskman.eionet.europa.eu/time_entries?utf8=%E2%9C%93&set_filter=1&sort=spent_on%3Adesc&f%5B%5D=spent_on&op%5Bspent_on%5D=%3E%3C&v%5Bspent_on%5D%5B%5D=2020-06-01&v%5Bspent_on%5D%5B%5D=2020-07-31&f%5B%5D=cf_36&op%5Bcf_36%5D=%3D&v%5Bcf_36%5D%5B%5D=eaudeweb-FISE-07.0202%2F2018%2F776035%2FSER%2FENV.D.1&f%5B%5D=&c%5B%5D=project&c%5B%5D=spent_on&c%5B%5D=user&c%5B%5D=activity&c%5B%5D=issue&c%5B%5D=comments&c%5B%5D=hours&group_by=&t%5B%5D=hours&t%5B%5D=).

# Issues (input from Issue Log)

Status: **Green**

# Risks (input from Risk Log)

Status: **Green**

# Activities Performed and Planned

Performed:

* Re-Implementation of the catalogue search in ESBootstrap, usage of the files on CMShare and synchronisations with list in csv
* Adapt Forest and wooded land text block on the homepage to use dynamic data
* Improvements for Plotly chart tool such as: axis, download feature etc.
* Site structure improvements - allow different topics sections under each country factsheet

Planned:

* Agree with EEA Project Manager on the future scope and prioritisation of work for FISE as the implementations will be ended at the end of August 2020; preparations for maintenance period
* Final report