# Project Progress

|  |  |  |  |
| --- | --- | --- | --- |
| Initiating | Planning | Executing | Closing |
|  | Monitor & Control |  |

**Overall Status: Green**

**Project Owner (PO): Cristina Brăilescu, DG ENV**

**Business Manager (BM):** **Beate Werner, EEA**

**Solution Provider (SP): Soren Roug, EEA**

**Project Manager (PM):** **Miruna Badescu, EdW**

# Milestones

08/07/18: Static portal with design

14/09/18: First test version of the infrastructure

17-18/09/18: FISE presentation in NRC meeting

28/02/19: First prototype ready for testing

31/12/19: Final prototype ready and operational ready

04/02/20: Launch of FISE

# Project Indicators

Schedule: **Green**

* Baselined delivery date: 02/2020
* Forecasted delivery date: 02/2020
* Variance: 0 months

Cost: **Green**

* Baselined: 1659 (1129 EdW+530 TRACASA) workdays
* Spent: 811 (558 EdW + 253 TRACASA) workdays
* Forecasted: 811 workdays
* Variance: 0% (Forecasted - Baselined)

# Project Changes (input from Change Log)

Status: **Green**

* Severe: 0

# Project Status Summary

Design adjustments and migration to Plone 5 is online <https://demo-forests-p5.eea.europa.eu/>, work is progressing on the import of datasets for Data Search (former NFI Search)

New set of data for Data (NFI) search functionality received from JRC up to 31/10/2019 will be imported into FISE.

There has been collaboration of all stakeholders in elaborating the requirements for the FISE prototype in regards to its launch in Jan/Feb 2020.

A technical meeting took place in EEA on 15th Oct (Eau de Web, Tracasa and EEA DIS) and future technical approaches have been identified and will be analysed for implementation.

Current stage of FISE implementation has been presented during NRC Forests meeting that took place on 16th October at EEA.

# Activities Performed and Planned

Performed:

* Enhancements for the portal design and logo proposal, improvements on usability and import of new data to Data (NFI) search
* Migration of the portal CMS to newer Plone 5 version and EEA KGS
* Establishment of the metadata element set for FISE content and information
* Meeting at DG ENV on 5th Sept 2019 with all stakeholders for design approval and decisions on the priorities for FISE Launch
* Meeting on 15th October 2019 for technical aspects of the FISE implementation
* Presentation of current FISE implementation during the NRC Forests meeting in EEA

Planned:

* Implementation of new content types in the portal: map, country factsheet, topic page etc.
* Finalisation of the design implementation, including feedback received
* Establish technical details and architecture for integration of maps and datasets
* Release of the platform in Dec 2019 and feedback collection and fixes until its launch in Feb 2020

# Risks (input from Risk Log)

Status: **Green**

* Active: 1 – Caution needs to be taken in development to use only official data and not interpret it in any way.

# Issues (input from Issue Log)

Status: **Green**