# Project Progress

|  |  |  |  |
| --- | --- | --- | --- |
| Initiating | Planning | Executing | Closing |
|  | Monitor & Control | |  |

**Overall Status: Green**

**Project Owner (PO): Cristina Brăilescu, DG ENV**

**Business Manager (BM):** **Beate Werner, EEA**

**Solution Provider (SP): Soren Roug, EEA**

**EEA Project Manager: Nils Hettich, EEA**

**EdW Project Manager (PM):** **Miruna Badescu, EdW**

**EdW Technical Lead: Mihai Macaneata, EdW**

# Milestones

08/07/18: Static portal with design

14/09/18: First test version of the infrastructure

28/02/19: First prototype ready for testing

31/12/19: Final prototype ready and operational ready

04/02/20: Launch of FISE prototype

31/08/20: Improvements and enhancements of the prototype

30/11/20: Maintenance of FISE

# Project Indicators

Schedule: **Green**

* Baselined delivery date: 08/2020
* Forecasted delivery date: 08/2020
* Variance: 0 months

Cost: **Green** (until 31/03/2020)

* Baselined: 1659 (1129 EdW+530 TRACASA) workdays
* Spent: 1267 (914 EdW + 353 TRACASA) workdays
* Forecasted: 1267 workdays
* Variance: 0% (Forecasted - Baselined)

# Project Changes (input from Change Log)

Status: **Green**

* Severe: 0

# Project Status Summary

EEA DIS1 took over the project management for FISE in Jan 2020 and is prioritizing and supervising all the implementations that are done for the launch of the FISE prototype.

All work that has been performed during the reporting period is discussed, prioritized and assigned in very close cooperation with EEA Project Manager. A complete list of activities can be consulted [here](https://taskman.eionet.europa.eu/time_entries?c%5B%5D=project&c%5B%5D=spent_on&c%5B%5D=user&c%5B%5D=activity&c%5B%5D=issue&c%5B%5D=comments&c%5B%5D=hours&f%5B%5D=spent_on&f%5B%5D=cf_36&f%5B%5D=&group_by=&op%5Bcf_36%5D=%3D&op%5Bspent_on%5D=%3E%3C&per_page=250&set_filter=1&sort=spent_on%3Adesc&t%5B%5D=hours&t%5B%5D=&utf8=%E2%9C%93&v%5Bcf_36%5D%5B%5D=eaudeweb-FISE-07.0202%2F2018%2F776035%2FSER%2FENV.D.1&v%5Bspent_on%5D%5B%5D=2020-02-03&v%5Bspent_on%5D%5B%5D=2020-03-31).

# Issues (input from Issue Log)

Status: **Green**

# Risks (input from Risk Log)

Status: **Green**

1. COVID-19 WHO pandemic may slow down deliveries: Both EEA and EdW personnel is working from home, according to national and European recommendations. EdW ensured all its personnel proper infrastructure and access to project’s resources.

# Activities Performed and Planned

Performed:

* Improvements of the mosaic tiles layouts for Volto toolkit
* Creation of PloneSaaS orchestration for FISE, automatic deployment for demo-forest frontend and other DevOp tasks
* Adding more options to customize number formatting, ability to choose and define multiple colour schemes for Plotly chart tool
* Adding news component to FISE and corresponding portlet
* Improve print layout for factsheets and include pdf download for factsheets, pdf download for dexterity types of content
* Revise and update the NFI repository and search functionality in FISE portal

Planned:

* Agree with EEA Project Manager on the future scope and prioritisation of work for FISE and their implementation (e.g.: search, catalogue, usage of JRC collected data, enhancements, improvements, export blocks in pdf, normalisation of data sources which feed the factsheets etc.)
* Improvements to the underlying components: Plone SaaS, Volto/Mosaic etc.
* Monthly status report