# Project Progress

|  |  |  |  |
| --- | --- | --- | --- |
| Initiating | Planning | Executing | Closing |
|  | Monitor & Control | |  |

**Overall Status: Green**

**Project Owner (PO): Cristina Brăilescu, DG ENV**

**Business Manager (BM):** **Beate Werner, EEA**

**Solution Provider (SP): Soren Roug, EEA**

**Project Manager (PM):** **Miruna Badescu, EdW**

# Milestones

08/07/18: Static portal with design

14/09/18: First test version of the infrastructure

17-18/09/18: FISE presentation in NRC meeting

28/02/19: First prototype ready for testing

31/12/19: Final prototype ready and operational ready

22/01/20: Launch of FISE

# Project Indicators

Schedule: **Green**

* Baselined delivery date: 12/2019
* Forecasted delivery date: 12/2019
* Variance: 0 months

Cost: **Green**

* Baselined: 1659 (1129 EdW+530 TRACASA) workdays
* Spent: 661 (465 EdW + 196 TRACASA) workdays
* Forecasted: 661 workdays
* Variance: 0% (Forecasted - Baselined)

# Project Changes (input from Change Log)

Status: **Green**

* Severe: 0

# Project Status Summary

First portal prototype with design adjustments is online <http://demo-forests.eea.europa.eu> , work is progressing on the import for Data Search (former NFI Search)

New set of data for Data (NFI) search functionality received from JRC up to 30/08/2019 will be imported into FISE.

There has been collaboration of all stakeholders in elaborating the work plan for the FISE prototype in regards to its launch in Jan 2020.

A technical meeting took place in EEA on 30th July (Eau de Web, Tracasa and EEA DIS) and future technical approaches have been identified and will be analysed for implementation.

Another meeting has been planned for 5th September at DG ENV for discussions and decision regarding FISE.

# Activities Performed and Planned

Performed:

* Enhancements for the portal and new logo proposal, improvements on usability and import of new data to Data (NFI) search, proposal for country pages
* Migration of the portal CMS to newer Plone 5 version and EEA KGS
* Establishment of the metadata element set for FISE content and information
* Technical meeting in EEA on 30th July 2019

Planned:

* Definition of new content types in the portal: map, country factsheet, topic page etc.
* Unified search functionality for FISE to include: EEA information, FISE content, JRC collected data etc.
* Meeting at DG ENV with all stakeholder on 5th September 2019
* Implementation of the new design in Plone 5

# Risks (input from Risk Log)

Status: **Green**

* Active: 1 – Caution needs to be taken in development to use only official data and not interpret it in any way.

# Issues (input from Issue Log)

Status: **Green**